## Meeting Logs
Meeting # | Date | Members Present | Issue Discussed | Meeting Results | Next Meeting Date
1 | 20/04/2026 | Rawan, Dima, Dana, Lama | Project topic selection and proposal | Selected Course Registration System. Agreed on main features and scope. | 24/04/2026
2 | 24/04/2026 | Rawan, Dima, Dana, Lama | Requirements gathering and analysis | Identified 16 functional and 8 non-functional requirements. Assigned team roles. | 28/04/2026
3 | 28/04/2026 | Rawan, Dima, Dana, Lama | System design and UML diagrams | Completed Use Case, Class, Sequence, and ER diagrams. Approved database design. | 02/05/2026
4 | 02/05/2026 | Rawan, Dima, Dana, Lama | Implementation progress review | Backend routes completed. Frontend templates in progress. Fixed blueprint issues. | 06/05/2026
5 | 06/05/2026 | Rawan, Dima, Dana, Lama | Testing phase | Completed unit and integration testing. Fixed 3 minor bugs. All tests passed. | 10/05/2026
6 | 10/05/2026 | Rawan, Dima, Dana, Lama | Final review and deployment | Project uploaded to GitHub. Report finalized. Ready for submission | -